**Annexure 2D: Quarter Progress Report**

Page 1

**Photo**

**Project SAMEIP**

Livelihoods- ABLE

**Quarter/Annual Progress Report**

June to September

WinVinaya Foundation, Bangalore

|  |  |
| --- | --- |
| Submitted By:  Name: Alwin Augustine  Designation: Project Coordinator  Organization Name and Logo: | Submitted to:  Name:  The American India Foundation Trust |

Page 2 onwards

1. Data Status :

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| **Livelihoods- ABLE** | | | | | | |
| **S.No** | **Centre’s Name** | **Training Type** | **Trained** | | **Employability Support** | |
| **Target** | **Achieved** | **Target** | **Achieved** |
| 1 | Bangalore | Software Development | 17 | 17 | 5 | 0 |
|  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |

1. **Project Progress Indicators:**

|  |
| --- |
| **Indicators** |
| # of Candidates enrolled: 22 |
| # of Candidates under training: Nil |
| # of Candidates dropped out:5 |
| # of Candidates completed training:17 |
| # of Job roles candidates trained on: Software Development |
| # of Companies reached out to: 10 |
| # of Companies/Organization hiring candidates from Program: In progress |
| # of Candidates employed: In progress |
| % of Candidates employed (completed training / employed): In progress |
| % of Candidates continued employment for 3 months: NA |
| % of Candidates continued employment for 6 months: NA |
| # of engagement activities held with key stakeholders: |

1. Major activities covered and on-going in the reporting period (From date To date)

|  |  |  |
| --- | --- | --- |
| 1 | Month- July | Photographs |
| A | Mobilization of candidates |  |
| B | Assessment of applicants |  |
| C | Pre-training Counselling |  |
| D | Training through WinVinaya Academy | <https://1drv.ms/u/s!AuC7xy_1TxOhgvgVICzmK1Af-ref8g?e=8mlw60> |
| 2 | Month- August | Photographs |
| A | Training through WinVinaya Academy | <https://1drv.ms/u/s!AuC7xy_1TxOhgvgVICzmK1Af-ref8g?e=8mlw60> |
| B | Mock Interviews for the candidates (Internal and external) | <https://1drv.ms/u/s!AuC7xy_1TxOhgvgWm9hENj2sPC97qg?e=8nQEI9> |
| C |  |  |
| 3 | Month- September | Photographs |
| A | Training through WinVinaya Academy |  |
| B | Started the training for new batches | <https://1drv.ms/u/s!AuC7xy_1TxOhgvgbzJhMpSFGMSiWaw?e=Z4hrUo> |
| C |  |  |

1. Challenges in delivering the program

|  |  |  |
| --- | --- | --- |
| Challenges , if any | What measures were adopted to overcome the challenges | What was the result? |
| a. Candidates faced issues with internet and infrastructure requirements for the training which resulted in few dropouts | We added infrastructure readiness session and career counselling session prior to the training for the new batches | Infrastructure readiness session helped to know about candidates’ issues with the internet and availability of laptop for the training.  Career Counselling helped to know about the candidates and to build the rapport prior to the training. |
| b. We didn’t had clarity on AIF documentation works | We got the reporting templates and guidelines from AIF | Now we have the knowledge about documentation works |

1. Stories of Success along with pictures (Please attach the consent form signed by the candidate while reporting any case study)

Case story of Prachi Pandey (B1 Batch) - <https://1drv.ms/w/s!AuC7xy_1TxOhgvgZcIa-WVx2hXfnvQ?e=1BxsdE>

Case story of Ambuj Pandey (B2 Batch) - <https://1drv.ms/w/s!AuC7xy_1TxOhgvgYeaS2U0iKNrkhxQ?e=PRFAnV>

1. Testimonials about disability rights
2. Beneficiaries quotes

*“WinVinaya Foundation is a very good because they provides the high level training. This software development training was very beneficial for me. Before attending this training, I had no much knowledge in Java, SQL and in also English communication etc. So I feel proud that I have successfully completed the training in WinVinaya*” – Rakesh kumar, Batch B3

*“I learned so much about Java and SQL in WinVinaya software development training. One of the main point is that they taught me how to communicate in English with confidence and this program was very helpful to develop my knowledge*” – Yogesh Kumar, Batch B3

1. Future Goals for next quarter
   * More emphasize on placement of candidates who completed the training
   * Completing the training for Batch from B4 to B10
   * Adding more external mock interviews sessions for the candidates
   * Sourcing more candidates to reduce the dropout rate